## Sheet1
Module |  | Start Date | Est Delivery Date | Status
Manage Qsa | Add/Edit/Delete/View |  |  | Done
Manage QA | Add/Edit/Delete/View |  |  | Done
Manage Consultants | Add/Edit/Delete/View |  |  | Done
Manage Customer | Add/Edit/Delete/View |  |  | Done
| Add Process |  |  | Done
| Edit Process |  |  | Done
| Generate Certificate |  |  | Done
Manage Compliance | Add/Edit/Delete |  |  | Done
| Assign Service to customer on his process |  |  | Done
View questionnair related service
show customer comment and document
Manage Questionnair | Edit questionnair according to service |  |  | Done
Customer Panel | Login customer using certificate
Forgot password
Dashboard (Process ,services)
Questionnair according to services
comment,upload document on questionnair
Qsa Panel | Login with its certificate
Showing Certificate customer details
Show questioonair
Comment on customer upload document
Mukesh Work
Module | Asign Work | Asign Date | Est Delivery Date | Status
2018-06-12
login QA and QSA | working in qsa and qa | 2018-06-12
login QA and QSA | testing in qsa and qa login | 2018-06-13
login QA and QSA | error solving in qsa and qa | 2018-06-14
2018-07-12
login QA,QSA,CUSTOMER,Consultant | testing whole panacea in login customer,qsa,qa consultant
Testing | after testing error solve panacea
Consutant login | testing in consultant login
2018-07-12
Login Customer | working at customer status
Login Customer | working at customer status
testing in panacea
error solves after coming error
2018-10-12
working at customer status
working at customer status
working at customer status
working at customer status
2018-11-12
code deploy in live server after testing
solve the error after coming error
working at changes status qsa
working at changes status qsa
working at status qsa
2018-12-12
working in admin login status
working in admin login of apporve, disapprove, mark incomplete and in progress
testing forstatus of all user login customerm qa , qsa , consultant and admin
solve the error in all login user
13/12/2018
Admin can upload the Report of Complience(ROC) .
Admin can upload Attestations of Complience(AOC).
If the all question will approved by Admin then status change Approved and if the all question are not approved then status is Inprogress in compliances listing.
testing in admin panel, qsa panel, qa panel , customer panel and consultant panel
Admin can approved, Disapproved, Mark incomplete and In Progress.
14/12/2018
show status in customer login
data fetch for sub customer in customer login
data fetch for sub qsa in qsa login
data fetch for sub qa in qa login
data fetch for sub consultant in consutant login
17/12/2018
working on testing complience login
change the delete,download customer and qsa login
testing panacea
remove the spacing between comments and icon chmage
18/12/2018
changes Message in the customer login, QSA login ,QA login, Consultant login and Admin login.
Minimum one file uploading in every user which will upload the file.
First see the uploaded document in customer login, QSA login ,QA login, Consultant login and Admin login.
After that comment in customer login, QSA login ,QA login, Consultant login and Admin login.
After status date and time in customer login, QSA login ,QA login, Consultant login and Admin login.
After that approve /disapprove/mark incomplete/in progress.
19/12/2018
status changes of customer login,qsa login, qa login and consultant login
request modification for admin in qa
accept and reject in admin login status changes
design chnages
testing panacea